STATEMENT OF WORK BETWEEN

Client

And

JMAN Group

1	Business Context

PURE FINANCIAL ADVISORS LLC operates in the United States, specializing in financial advisory and asset management services. As a B2C firm, PURE engages with individual clients, supported by key stakeholders such as Jason Carver (Client Engagement Manager) and Lee Equity Partners (investment partner). The organization relies on a robust technology stack, including Salesforce, Tamarac, Azure Blob Storage, Microsoft Fabric, Azure Synapse, Power BI, and is preparing to integrate QuickBooks for improved financial tracking and reporting.

Driven by the need for greater transparency and actionable insights, PURE aims to develop a comprehensive Lead-to-AUM (L2A) pipeline and Customer Acquisition Cost (CAC) reporting solution. The current pain points include limited granularity in pipeline reporting and an absence of integrated CAC insights. Addressing these gaps is expected to provide a deeper understanding of the journey from lead to AUM and enhance visibility into marketing ROI, thereby supporting data-informed decisions for senior leadership and marketing teams.

This initiative is strategically significant for PURE’s ongoing growth and data maturity, enabling scalable reporting capabilities and improving Power BI dashboards with clear KPI definitions and visualizations. By automating data ingestion and transformation processes and ensuring solid integration with Salesforce and QuickBooks, PURE will gain accurate, timely insights into its business performance. These improvements are critical to maintaining competitive advantage and optimizing marketing spend, underpinned by a scalable, future-ready data platform.

2	Overview

PURE FINANCIAL ADVISORS LLC’s operations related to pipeline and customer acquisition reporting currently involve the data, technology, and marketing teams. These groups collaborate to manage and analyze information critical to tracking the lead-to-AUM (L2A) pipeline and customer acquisition cost (CAC) metrics.

Key systems supporting these processes include Salesforce and Tamarac for customer and asset data, Azure Blob Storage for scalable data storage, and Power BI as the primary analytics and reporting suite. Microsoft Fabric and Azure Synapse serve as the core cloud-based data platforms underpinning data integration, storage, and transformation activities. QuickBooks is also identified as a relevant data source, with ongoing initiatives to better connect and ingest its data for CAC reporting purposes.

At present, Power BI is leveraged for reporting, enabling the organization to visualize and monitor performance based on integrated data from Salesforce, Tamarac, and Azure platforms. There are active integration efforts focused on establishing data flows from QuickBooks while ensuring the quality of data ingested for reporting needs. The existing technology environment relies on batch processing for data pipelines within the Fabric data platform.

3	Understanding

•	Limited granularity in existing pipeline reporting hampers the ability to analyze the full customer journey from lead to AUM and accurately assess marketing effectiveness.

•	Absence of integrated Customer Acquisition Cost (CAC) reporting prevents clear measurement of return on marketing investment.

•	Requirement for enhanced Lead-to-AUM (L2A) and CAC data models to provide greater detail and actionable insights for leadership and marketing teams.

•	Prompt need for automated data ingestion and transformation pipelines, specifically to support batch processing of L2A and CAC metrics.

•	Mandatory integration with QuickBooks and Salesforce is required to ensure all relevant data is available for accurate pipeline and CAC analysis.

•	Data quality assessment is a critical requirement to ensure the accuracy and reliability of insights derived from combined sources.

•	The system must support data and technology stakeholders, senior leadership, and marketing teams who depend on accurate, timely reporting for decision-making.

•	Engagement is contingent on timely access to Salesforce, QuickBooks, and existing Microsoft Fabric and Azure Synapse platforms for successful delivery.

4	Objectives

•	Deliver a comprehensive Lead-to-AUM (L2A) and Customer Acquisition Cost (CAC) data model and reporting suite that provides granular insights into pipeline performance and marketing ROI.

•	Automate data ingestion, transformation, and reporting refresh processes to ensure timely and accurate information.

•	Empower leadership with detailed visibility into the customer journey from lead to AUM and clear metrics on marketing effectiveness.

•	Enhance user experience through improved Power BI dashboards featuring clear KPI definitions and interactive visualizations.

•	Advance the maturity and scalability of PURE’s reporting capabilities to support future data sources and evolving analytical needs.

•	Ensure seamless integration with Salesforce, QuickBooks, Tamarac, and Microsoft Fabric to enable unified and reliable data flows.

5	Deliverables

Throughout the engagement with PURE FINANCIAL ADVISORS LLC, the following key deliverables and artifacts will be provided to ensure a comprehensive and actionable outcome aligned with the project objectives:

1. KPI Book

•	Comprehensive documentation of all metrics and Key Performance Indicators (KPIs) for Lead-to-AUM (L2A) and Customer Acquisition Cost (CAC) reporting.

•	Detailed definitions, calculation logic, and business context for each KPI.

•	Delivered in electronic document format (PDF/Word), serving as the reference standard for all metrics.

•	Delivered at the end of the initial discovery phase (Phase 3A).

2. Power BI Mock-ups

•	Visual prototypes of the enhanced L2A and CAC dashboards, limited to eight distinct report views.

•	Includes proposed layouts, data visualizations, and user workflows for key reporting scenarios.

•	Provided in interactive Power BI format and supplementary image snapshots (PDF/PNG).

•	Delivered iteratively by the midpoint and completion of Phase 3A.

3. Data Model Design

•	Detailed conceptual and logical data models for enhanced L2A and CAC reporting.

•	Entity-relationship diagrams, data flow designs, and data mapping documents.

•	Delivered in diagrammatic (Visio or similar tool) and documentation formats.

•	Draft delivered during Phase 3A, with final version at phase close.

4. Data Gap Assessment

•	Identification and analysis of any gaps in current data sources, including completeness, quality, and integrity specifically for QuickBooks, Salesforce, and other relevant systems.

•	Recommendations for addressing data issues and mitigating integration risks.

•	Delivered as a written report (PDF/Word).

•	Provided by the end of Phase 3A.

5. Technical Approach

•	Comprehensive guidance on solution architecture, technology integration, and automation strategies for data ingestion and transformation from QuickBooks and Salesforce into Microsoft Fabric.

•	Detailed technical requirements, integration flowcharts, and implementation considerations.

•	Delivered as a technical design document (PDF/Word).

•	Completed by the conclusion of Phase 3A.

6. Phase 3B Implementation Plan

•	Sequenced roadmap outlining activities, milestones, roles, and dependencies for the build and rollout of the new L2A and CAC reporting solution.

•	Includes timelines, resource allocation, risk mitigation steps, and change management considerations.

•	Delivered as a project plan document (PDF/Word or MS Project format).

•	Presented at the close of Phase 3A for client review and alignment prior to Phase 3B kickoff.

Each deliverable will be iteratively reviewed with PURE FINANCIAL ADVISORS LLC’s leadership and technical teams to ensure alignment with business goals and to incorporate feedback promptly. This structured approach guarantees transparency, accountability, and measurable value throughout the engagement lifecycle.

6	Approach

PURE FINANCIAL ADVISORS LLC aims to enhance its Lead-to-AUM (L2A) and Customer Acquisition Cost (CAC) pipeline reporting, providing deeper visibility into client acquisition and marketing return on investment. Central to this engagement is the development of a scalable, integrated data model and reporting suite leveraging existing platforms—Microsoft Fabric, Azure Synapse, Power BI—and seamless integration of QuickBooks and Salesforce data. Our methodology is grounded in structured discovery, data-centric design, and agile build practices, ensuring alignment with defined business objectives and stakeholder needs.

The approach is organized into two core phases. Phase 3A focuses on design and requirements definition, laying the foundation for robust reporting and KPI logic. Phase 3B encompasses implementation, including building automated data pipelines, integrating QuickBooks, enhancing data quality, and configuring advanced Power BI dashboards. This phased plan facilitates risk management, stakeholder engagement, and incremental value delivery—culminating in actionable insight for senior leadership and marketing teams.

---

Phase 3A: Discovery & Design, Duration: 3 weeks, Timeline: Week 1 to Week 3

Summary: This phase establishes and documents the foundational requirements, data logic, and reporting structures necessary for effective L2A and CAC analytics.

Activities:

•	Conduct stakeholder workshops with Data, Technology, and Marketing teams to refine reporting needs

•	Analyze source systems (Salesforce, Tamarac, Azure Blob Storage, QuickBooks) for data model compatibility and gaps

•	Design the integrated L2A and CAC data models, specifying KPI logic and business calculation rules

•	Develop Power BI mock-ups (up to 8 views), incorporating key workflows and visualizations

•	Assess data quality for pipeline and CAC metrics to identify cleansing and transformation requirements

•	Prepare a Phase 3B Implementation Plan detailing technical steps, dependencies, and roadmap

---

Phase 3B: Solution Build & Integration, Duration: 8–12 weeks, Timeline: Week 4 to Week 15

Summary: This phase delivers the operational solution, including automated pipelines, integrations, data assurance measures, and actionable Power BI dashboards.

Activities:

•	Build and automate batch data ingestion pipelines on Microsoft Fabric for L2A and CAC reporting, integrating Salesforce and QuickBooks

•	Implement data transformation and quality assurance routines within Azure Synapse

•	Deploy the new L2A and CAC data model to the reporting environment, ensuring scalability and governance

•	Configure and publish Power BI dashboards, refining KPI definitions and visual interactions for end-users

•	Test end-to-end data flow, aligning metrics with business requirements and addressing integration challenges

•	Conduct user training and provide documentation to support adoption and change management

---

By following this structured, phased approach, PURE FINANCIAL ADVISORS LLC will achieve a scalable, insightful reporting solution that improves data-driven decision making and marketing ROI analysis. Each phase is designed to build on the previous, minimizing risk and maximizing stakeholder ownership, ensuring the solution meets both current and future business needs.

7	Outcomes

The proposed engagement will advance PURE FINANCIAL ADVISORS LLC’s data maturity by delivering an automated, integrated reporting suite focused on Lead-to-AUM (L2A) and Customer Acquisition Cost (CAC) metrics. This initiative will provide actionable and granular insights, enabling data-driven decisions that improve marketing efficiency and pipeline performance. By equipping leadership and key business teams with enriched analytics, PURE will gain a transparent view of the client journey and realize greater returns on marketing investments.

Expected Business Outcomes

•	Improved Pipeline Visibility: Attain a detailed, end-to-end understanding of the conversion journey from initial lead through to assets under management, empowering teams to identify and address bottlenecks in the acquisition funnel.

•	Actionable CAC Insights: Deliver accurate, timely, and integrated reporting on Customer Acquisition Cost, allowing for precise measurement of marketing spend effectiveness and aiding resource allocation strategies.

•	Enhanced Data-Driven Decision Making: Enable leadership and key stakeholders to make informed, evidence-based decisions using clearly defined KPIs, ongoing data quality assessments, and robust Power BI dashboards.

•	Automated Reporting & Data Processes: Reduce manual effort and margin for error by implementing automated ingestion, transformation, and reporting refreshes, resulting in more consistently up-to-date analytics.

•	Scalable Analytics Infrastructure: Lay the groundwork for sustainable growth by building a reporting platform that can seamlessly integrate future data sources and scale with business needs.

•	Marketing ROI Optimization: Support continuous improvement in marketing strategies by providing transparent, real-time insights into the return on marketing investment, increasing accountability and performance across campaigns.

8	Business Impact

•	Enhanced Financial Transparency and ROI Accountability: The solution delivers automated and granular Lead-to-AUM (L2A) and Customer Acquisition Cost (CAC) reporting, providing PURE FINANCIAL ADVISORS LLC with clear visibility into pipeline performance and marketing spend effectiveness. This enables leadership to quantify marketing ROI, directly connecting campaign expenditures to asset growth and client acquisition metrics.

•	Reduction in Manual Reporting Effort: By automating data ingestion and transformation pipelines across Salesforce, QuickBooks, Tamarac, and Azure Fabric, the need for manual report assembly is eliminated. Batch processing and Power BI dashboard refreshes drastically reduce manual effort, speeding up reporting cycles and freeing up staff resources for higher-value analytical work.

•	Strategic Decision Support with Granular Insights: Leadership gains access to a robust data model and KPI logic that informs pivotal decisions—such as optimizing marketing investments or targeting client segments. The detailed L2A tracking empowers PURE to identify conversion bottlenecks and calibration opportunities, supporting strategic growth initiatives.

•	Scalable and Future-Proof Data Platform: The integrated design leverages Microsoft Fabric and Azure Synapse for scalable data processing and reporting. The architecture supports future expansion to new data sources and evolving business needs, ensuring long-term operational efficiency and adaptability.

•	Competitive Advantage through Advanced Analytics: The enhanced Power BI reporting suite advances PURE’s data maturity, setting it apart within the financial advisory sector. Providing actionable insights and real-time KPI visualizations enables PURE to demonstrate superior transparency and responsiveness to both clients and investment partners.

The proposed initiative will markedly improve PURE FINANCIAL ADVISORS LLC’s ability to monitor, optimize, and scale its client acquisition workflows. By integrating automated, insightful L2A and CAC reporting across core business systems, PURE will gain operational efficiency, financial clarity, and strategic agility, positioning the firm for sustained growth and competitive leadership in the US wealth management industry.